## Sheet1
BOSTON COMMUNITY IMPROVEMENT DISTRICT (Boston CID) IMPLEMENTATION PLAN July 2022 - June 2023
PROGRAMME 1: GOVERNANCE, MANAGEMENT & OPERATIONS
No. | Action | Responsibility | Frequency | Duration |  |  |  |  | Performance Indicator | Comments
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
1.1 | Register Boston CID NPC with CIPC | Steering Committee | Once | 1 | 0 | 0 | 0 | 0 | NPC issued CIPC documents
1.2 | Elect Chairman and assign portfolios | Steering Committee | Once | 1 | 1 | 1 | 1 | 1 | First meeting of board of directors | This is done annually after the AGM
1.3 | Open Bank Account for Boston CID | Treasurer | Once | 1 | 0 | 0 | 0 | 0 | Bank account opened
1.4 | Apply to SARS for tax exemption. | Steering Committee | Once | 1 | 0 | 0 | 0 | 0 | Receipt of Tax Exemption Certificate before end of FY1
1.5 | Register for VAT | Steering Committee | Once | 1 | 0 | 0 | 0 | 0 | Receipt of VAT Registration Number
1.6 | Submit Supplier Application | Steering Committee | Once | 1 | 0 | 0 | 0 | 0 | Receipt of Vendor Number
1.7 | Register as a Community Based Organisation (CBO) with the CCT | Secretary | Once | 1 | 0 | 0 | 0 | 0 | Receipt of CBO registration within first year of operation | First 6 months of operation not done during that period.
1.8 | Secure CID Offices | Steering Committee | Annually | 1 | 1 | 1 | 1 | 1 | Operational and signed rental agreement | Rental agreement with Sujean property investments
1.9 | Appoint CID Manager | Steering Committee | Once | 1 | 0 | 0 | 0 | 0 | Suitable person found fitting the job description, character and aptitude | Review performance annually
1.1 | Hold 1st Members Meeting | Chairman & Secretary | Annually | 1 | 0 | 0 | 0 | 0 | First Members Meeting to be held within 6 months of | Object of meeting is to elect Board members, to approve next year’s
[9 empty] | registration as a NPC. Signed minutes. | Implementation Plan, and to approve next year’s budget
1.11 | Hold Annual General Meeting | Secretary | Annually | 0 | 1 | 1 | 1 | 1 | AGM held to report back to members, elect directors, approve next year’s implementation plan and budget, appoint auditors and appoint company secretary | Before end of December annually
1.12 | Submit Financial Reports to the Board. | Treasurer | Monthly | 12 | 12 | 12 | 12 | 12 | Monthly Financial Reports submitted to board members | Review bank statements. Monitor creditors/debtors monthly. Pay creditors. Review monthly income from City. Prepare monthly management accounts
1.13 | Draw up and submit monthly Financial reports to CCT | Treasurer | Monthly | 12 | 12 | 12 | 12 | 12 | Monthly financial reports lodged with CID Department by 15th of the following month | Submit reports timeously via the apointed service provider by 15 of each month.
1.14 | Report to Board on CID Arrears | Treasurer | Monthly | 12 | 12 | 12 | 12 | 12 | Observe and report concern over outstanding amounts | Directors in arrears may not take part in board meetings
1.15 | Annual Financial Statement | Treasurer | Annually | 1 | 1 | 1 | 1 | 1 | Submit Audited AFS to CID department by 31 August | First 6 months of operation not done during that period.
1.16 | Submit Chairperson’s Report and AFS to local council. | Treasurer | Annually | 1 | 1 | 1 | 1 | 1 | Within 3 months of AGM submit Annual Report and AFS to subcouncil | First 6 months of operation not done during that period.
1.17 | CIPC compliance | Treasurer (using appointed bookkeeper) | Annually | 1 | 1 | 1 | 1 | 1 | CIPC Annual submissions lodged and Boston CID NPC issued with CIPC complete registration documents. | Register auditors with CIPC within 10 business days of appointment. Register/Unregister directors within 10 business days of appointment of new directors Submit annual returns within 30 days of anniversary of registration Maintain membership list
1.18 | Obtain SARS Tax Clearance Certificate | Treasurer | Annually | 1 | 1 | 1 | 1 | 1 | Annual Tax Clearance Certificate received from SARS; submit form to CCT | Obtain Tax Clearance Certificate from SARS one month before expiry of previous Tax Clearance Certificate
1.19 | Ensure VAT Compliance | Treasurer | Bi-Monthly | 6 | 6 | 6 | 6 | 6 | Submit VAT reconciliation to SARS bi-monthly
1.2 | Ensure Tax Compliance | Treasurer | Annually | 1 | 1 | 1 | 1 | 1 | Submit tax returns annually.
1.21 | Integrated Development Plan | Board/Secretary | Annually | 1 | 1 | 1 | 1 | 1 | Submit input to the Integrated Development Plan to subcouncil Manager in Oct-Feb annually.
1.22 | City Capital/Operating Budget | Board/Secretary | Annually | 1 | 1 | 1 | 1 | 1 | Submit input to the City Capital/Operating Budget to the subcouncil Manager by September annually.
1.23 | Conduct Board Meetings | Chairman - Secretary | Monthly | 12 | 12 | 12 | 12 | 12 | Signed Minutes of Monthly board meetings | First 30 minutes of the meeting will be open to the public
1.24 | Perform Mid -Year Budget Review. | Treasurer | Month six of financial Year | 1 | 1 | 1 | 1 | 1 | Budget mid-year review submitted to CID Department by 28 February
1.25 | Review CID Performance Mid- Year | Secretary | Month six of financial Year | 1 | 1 | 1 | 1 | 1 | Business Plan performance mid- year review submitted to CID Department by 28 February | As approved by the Board
1.26 | Submit Annual CID Implementation Plan and Budget | Board/Secretary/ Treasurer | Annually | 1 | 1 | 1 | 1 | 1 | Submit each year a draft updated annual implementation plan and budget to the CID Department for verification. Presented for approval by the members the annual implementation plan and budget at the AGM. | Submit to obtain approval as part of the CCT budget process
1.27 | Renewal Application for CID | Board/Secretary/ Treasurer | Last Year of Five Year Plan | 0 | 0 | 0 | 0 | 1 | Boston CID Term 2 Business Plan approved by Members at AGM submitted to CCT for approval.
1.28 | Manage the day-to-day operations of the CID effectively | Portfolio Directors (via CID Manager) | Ongoing | → | → | → | → | → | Report monthly at Board Meetings on CID implementation plan progress which includes management accounts and operations reports per portfolio
1.29 | Manage and monitor the service requests (C3) process | Portfolio Directors | Ongoing | → | → | → | → | → | Complete reports of service requests (C3), monitor existing issues and report to Board
1.3 | Build working relationships with subcouncil manager and relevant CCT department that deliver services in the CID | Portfolio Directors | Ongoing | → | → | → | → | → | Successful and professional relationships with subcouncil manager and officials resulting in enhanced communication, cooperation and service delivery
1.31 | Evaluate Service Providers | Portfolio Directors (via CID Manager) | Ongoing | → | → | → | → | → | Submit monthly report to Board
BOSTON COMMUNITY IMPROVEMENT DISTRICT (Boston CID) IMPLEMENTATION PLAN July 2022 - June 2023
PROGRAMME 2: PUBLIC SAFETY - VEHICULAR PATROLLING
No. | Action | Responsibility | Frequency | Duration |  |  |  |  | Performance Indicator | Comments
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
2.1 | Develop a Security Management Strategy Plan with clear deliverables and defined performance indicators to guide safety services by the appointed service provider and evaluate levels of service provided. | Public Safety Portfolio Director (with CID Manager) | Revise as often as required but at least quarterly | 3M | 3M | 3M | 3M | 3M | Documented Security Management Strategy Plan with clear deliverables and defined performance indicators to guide safety services by the appointed service provider and evaluate levels of service provided. | This is done comprehensively when a new Service Provider is (re)appointed and then modified continuously.
2.2 | Liaise with the relevant role players of other CIDs, BNW, SAPS, Security Agencies when required | Public Safety Portfolio Director (with CID Manager) | Ongoing | → | → | → | → | → | Monthly meetings | Meetings are conduted weekly with SAPS, BNHW, CID and security providers.
2.3 | Determine the Public Safety Patterns of the CID area in conjunction with the service providers, other CIDs, BNW and SAPS. | Public Safety Portfolio Director (with CID Manager) | Ongoing | → | → | → | → | → | Incorporate into Security Management Strategy Plan | Public safety paterns are identified and comunicated to relevant parties
2.4 | Set up and communicate Security number and/or communication channel to service provider | Public Safety Portfolio Director and Communications Portfolio Director (with CID Manager) | Ongoing | → | → | → | → | → | Provide residents with a contact number and procedure. | Dedicated phone line and Wapp number at controll room for communication
2.5 | Appoint security vehicle patrol provider | Public Safety Portfolio Director | Once every 4 years | 1 | 0 | 0 | 1 | 0 | The service contract is clear and unambiguous and meets the requirements of a stringent
|  | (together with CID Manager) | [6 empty] | performance specification. The Contractor is appointed for a period of four-year. A new contract is entered into in year 4
2.6 | Monitor performance of appointed security vehicle patrol provider | Public Safety Portfolio Director (via CID Manager) | Performance is measured once a month | 12 | 12 | 12 | 12 | 12 | Performance of the service providers is measured against the requirements of the service contract. A report is submitted to the Board and AGM | Performance is measured montly with FADT management.
2.7 | Collect, collate and communicate relevant security incidents to the Board | Public Safety Portfolio Director (via CID Manager) | Incidents and performance are reported once a month | 12 | 12 | 12 | 12 | 12 | The Board receives monthly reports of security incidents, trends and suggestions. Info is shared with BNW and SAPS. | Report findings to Board with recommendations where applicable.
2.8 | Regular Security Reports from Contract Security Company | Security Service Provider | Daily, Weekly | 1W | 1W | 1W | 1W | 1W | Report findings to Boston CID Board with recommendations where applicable. Provide feedback to forum meeting. | Daily, Weekly and montly reports submitted to CID Manager from FADT Contract Manager.
BOSTON COMMUNITY IMPROVEMENT DISTRICT (Boston CID) IMPLEMENTATION PLAN July 2022 - June 2023
PROGRAMME 3: PUBLIC SAFETY - SECURITY CAMERA NETWORK AND MONITORING
No. | Action | Responsibility | Frequency | Duration |  |  |  |  | Performance Indicator | Comments
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
3.1 | Appoint camera installation contractor | Public Safety Portfolio Director (with CID Manager) | Once | 1 | 0 | 0 | 0 | 0 | The contractor is appointed after competitive process
3.2 | Map out locations/specs for additional cameras. Oversee installation | Public Safety Portfolio Director (together with CID Manager) | Spread over 5 years | 1 | 1 | 1 | 1 | 1 | Location and type of cameras are decided in conjunction with the security service provider, BNW, other CIDs and SAPS. | Incorporate into Security Management Strategy Plan and monthly reports.
3.3 | Appoint camera monitoring/analytics provider | Public Safety Portfolio Director (together with CID Manager) | Once every 4 years | 1 | 0 | 0 | 1 | 0 | The service contract is clear and unambiguous and meets the requirements of a stringent performance specification. The Contractor is appointed for a period of four-years. A new contract is entered into in year 4
3.4 | Monitor performance of appointed camera installation and monitor providers | Public Safety Portfolio Director (via CID Manager) | Performance is measured once a month | 12 | 12 | 12 | 12 | 12 | Performance of the service providers is measured against the requirements of the service contract. A report is submitted to the Board and AGM
BOSTON COMMUNITY IMPROVEMENT DISTRICT (Boston CID) IMPLEMENTATION PLAN July 2022 - June 2023
PROGRAMME 4: PUBLIC SAFETY – FENCING, ACCESS CONTROL AND LIGTHING
No. | Action | Responsibility | Frequency | Duration |  |  |  |  | Performance Indicator | Comments
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
4.1 | Map out locations/specs for fencing and/or access control. Oversee installation | Public Safety Portfolio Director (together with CID Manager) | Spread over 5 years | 1 | 1 | 1 | 1 | 1 | Location and type of fencing are decided in conjunction with the security service provider, BNW, other CIDs and SAPS. | Incorporate into Security Management Strategy Plan
4.2 | Obtain necessary permission for fencing and/or access control. | Public Safety Portfolio Director (together with CID Manager) | Spread over 5 years | 1 | 1 | 1 | 1 | 1 | Coordinate and liaise with CCT on regulations, restrictions and permission.
4.3 | Map out locations/specs for additional lighting. Oversee installation | Public Safety Portfolio Director (together with CID Manager) | Spread over 5 years | 1 | 1 | 1 | 1 | 1 | Location and type of lighting is decided in conjunction with the security service provider, BNW, other CIDs and SAPS. | Incorporate into Security Management Strategy Plan
4.4 | Coordinate access control of parks and other areas | Public Safety Portfolio Director (via CID Manager) | Ongoing | → | → | → | → | → | Parks and access controlled areas are locked and opened at regular and communicated times | Obtain necessary permission. Incorporate into Security Management Strategy Plan
BOSTON COMMUNITY IMPROVEMENT DISTRICT (Boston CID) IMPLEMENTATION PLAN July 2022 - June 2023
PROGRAMME 5: CLEANING MANAGEMENT
No. | Action | Responsibility | Frequency | Duration |  |  |  |  | Performance Indicator | Comments
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
5.1 | Appoint contractor for cleaning program (local NGO) | Cleaning Portfolio Director (with CID Manager) | Once every 4 years | 1 | 0 | 0 | 1 | 0 | The contractor is appointed after competitive process. | Make use of local NGO MES
5.2 | Monitor performance of appointed providers | Cleaning Portfolio Director (via CID Manager) | Performance is measured once a month | 12 | 12 | 12 | 12 | 12 | Performance of the service providers is measured against the requirements of the service contract. A report is discussed with the service provider and submitted to the Board and AGM
5.3 | Oversee programme of cleaning | Cleaning Portfolio Director (via CID Manager) | Once per year | 1 | 1 | 1 | 1 | 1 | Performance of the service provider(s) is measured against the requirements of the service contract. A report is submitted to the Board and AGM | Oversee Cleaners on a daily basis report montly to Board
5.4 | Liaise with CCT to coordinate and ensure cleaning remains a top-up service | Cleaning Portfolio Director (via CID Manager) | Quarterly | 4 | 4 | 4 | 4 | 4 | CID resources are used optimally
BOSTON COMMUNITY IMPROVEMENT DISTRICT (Boston CID) IMPLEMENTATION PLAN July 2022 - June 2023
PROGRAMME 6: SOCIAL ISSUES MANAGEMENT
No. | Action | Responsibility | Frequency | Duration |  |  |  |  | Performance Indicator | Comments
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
6.1 | Work with local NGO’s and CCT Social Programmes to draw down opportunities and resources for social responsibility projects | Board & CCT Departments (together with CID Manager) | Ongoing | → | → | → | → | → | CCT Social Project Partnerships established. Contracts and agreements are well documented. Monthly reports are submitted to the Board
6.2 | Work with local NGO’s, neighbouring CIDs and organisations to coordinate efforts specifically related to the homeless | Social Responsibility Portfolio Director (together with CID Manager) | Initial setup completed during the first 6-month period and then monitored for performance | 12 | 12 | 12 | 12 | 12 | Agreements executed between all the relative entities, and compliance monitored beyond that. Specific monitoring of the homeless. | Coordinate with neigbouring CID and support local NGOs
6.3 | Work with local NGO’s, neighbouring CIDs and organisations to coordinate efforts specifically related to a. Drug and alcohol abuse b. Prostitution c. Vulnerable adults and children | Social Responsibility Portfolio Director (together with CID Manager) | Initial setup completed during the first 6-month period and then monitored for performance | 12 | 12 | 12 | 12 | 12 | Agreements executed between all the relative entities, and compliance monitored beyond that
6.4 | Collect, collate and communicate relevant Social Issue information to residents | Communications Portfolio Director (with CID Manager) | Ongoing | → | → | → | → | → | Regular reports, contact numbers and projects/opportunities communicated | Communicate with MES Sosial department
BOSTON COMMUNITY IMPROVEMENT DISTRICT (Boston CID) IMPLEMENTATION PLAN July 2022 - June 2023
PROGRAMME 7: URBAN MANAGEMENT (INCL. TRAFFIC)
No. | Action | Responsibility | Frequency | Duration |  |  |  |  | Performance Indicator | Comments
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
7.1 | Collect, collate and communicate problem areas with respect to:  missing drain covers / cleaning of drains  maintenance of road surfaces; sidewalks  cutting of grass / removal of weeds  road markings / traffic signs | Urban Management Portfolio Director (via CID Manager) | Ongoing | → | → | → | → | → | Regular monthly report findings to Boston CID Board with recommendations where applicable. Provide feedback to forum meeting.
7.2 | Coordinate and oversee repairs & maintenance by CCT | Urban Management Portfolio Director (via CID Manager) | Ongoing | → | → | → | → | → | Contract with professional firebreak inspectors to inspect the firebreaks and report to the Environmental PM and the Board
7.3 | Collect, collate and communicate relevant traffic (specifically taxi) related incidents to the Board | Public Safety Portfolio Director (via CID Manager) | Incidents and trends are reported once a month | 12 | 12 | 12 | 12 | 12 | The Board receives monthly reports of traffic related incidents, trends and suggestions. Info is shared with BNW and law enforcement authorities. | Incorporate into Security Management Strategy Plan
BOSTON COMMUNITY IMPROVEMENT DISTRICT (Boston CID) IMPLEMENTATION PLAN July 2022 - June 2023
PROGRAMME 8: COMMUNITY SPIRIT MANAGEMENT
No. | Action | Responsibility | Frequency | Duration |  |  |  |  | Performance Indicator | Comments
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
8.1 | Collect, collate and communicate relevant Community Spirit information to residents | Communications Portfolio Director (with CID Manager) | Ongoing | → | → | → | → | → | Regular updates and projects/opportunities communicated
BOSTON COMMUNITY IMPROVEMENT DISTRICT (Boston CID) IMPLEMENTATION PLAN July 2022 - June 2023
PROGRAMME 9: ENVIRONMENTAL MANAGEMENT
No. | Action | Responsibility | Frequency | Duration |  |  |  |  | Performance Indicator | Comments
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
9.1 | Work with local Parks and CCT to draw on opportunities and resources for environmental projects | Board & CCT Departments (together with CID Manager) | Ongoing | → | → | → | → | → | CCT Environmental Partnerships established. Contracts and agreements are well documented. Monthly reports are submitted to the Board | Work with Anneke Benskin form Parks Department.
9.2 | Establish an Environmental Strategy Plan for the CID area. | Environmental Management Portfolio Director (together with CID Manager) | Ongoing | → | → | → | → | → | Regular monthly report findings to Boston CID Board with recommendations where applicable. Provide feedback to forum meeting. | Turning Boston into a ‘leafy suburb’.
9.3 | Monitor CCT services and place C3 requests accordingly | Environmental Management Portfolio Director (together with CID Manager) | Ongoing | → | → | → | → | → | Ensure CCT services are rendered as agreed. | Mowing +/-9 cycles per year Tree pruning as per C3 requests Tree removal requests inspected as received. Removals directed by our tree policy Watering of newly planted trees being done with water tankers/trucks Maintenance/cleaning of Parks being done twice a week by the maintenance teams Weeding of flower beds being done by staff as required.
9.4 | Work with local organisations (Greater Tygerberg Partnership), neighbouring CIDs and companies to coordinate efforts specifically related to the recycling | Environmental Management Portfolio Director (together with CID Manager) | Ongoing | → | → | → | → | → | Agreements executed between all the relative entities, and compliance monitored beyond that. Specific monitoring of recycling.
9.5 | Collect, collate and communicate relevant Environmental information to residents | Communications Portfolio Director (with CID Manager) | Ongoing | → | → | → | → | → | Regular updates and projects/opportunities communicated
BOSTON COMMUNITY IMPROVEMENT DISTRICT (Boston CID) IMPLEMENTATION PLAN July 2022 - June 2023
PROGRAMME 10: COMMUNICATIONS
No. | Action | Responsibility | Frequency | Duration |  |  |  |  | Performance Indicator | Comments
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
10.1 | Establish and maintain a website | Communications Portfolio Director | Ongoing | → | → | → | → | → | Website published with all relevant documents as required by the SRA by-laws and policy
10.2 | Establish and maintain a Facebook page | Communications Portfolio Director | Ongoing | → | → | → | → | → | Communicate all relevant and current information
10.3 | Communicate with property owners and residents | Communications Portfolio Director | Ongoing | → | → | → | → | → | Newsletters are emailed every three months. Website is kept up to date. Upcoming meetings are advertised, and minutes are emailed. WhatsApp and Facebook groups are established as required | Board meetings: 1st 30 mins open to contributions from property owners.
10.4 | Collect, collate and communicate relevant information from residents to Board | Communications Portfolio Director | Ongoing | → | → | → | → | → | Regular monthly report findings to Boston CID Board with recommendations where applicable.
10.5 | Boston CID membership | Communications Portfolio Director | Ongoing | → | → | → | → | → | All property owners aware that membership does not happen by default; but that they must apply for such in order to qualify for voting status. Application for membership is displayed prominently on the website. Membership list is kept up to date | Membership is representative of property owners from the area
10.6 | Represent the CID community at various forums | Communications Portfolio Director | Ongoing | → | → | → | → | → | Liaise with different forums and address matters that have or can have an impact on the CID area, property owners and residents. Successful and professional relationship resulting in enhanced communication, cooperation and service delivery. Report to the Board.
10.7 | Boston CID branding | Communications Portfolio Director | Annually | 1 | 1 | 1 | 1 | 1 | Considerate placement of signage/branding in CID area
10.8 | Communicate with residents and property owners.  Newsletters  Website  Emails  Facebook  WhatsApp  Meetings | Communications Portfolio Director | Ongoing | → | → | → | → | → | Keep residents and property owners informed.